## Overview
Bug ID | Sprint | Test Case ID | Modül | Hata Türü | Açıklama | Severity | Priority | Durum | Tespit Tarihi | Çözüm Tarihi | Notlar
BR-01 | 2 | TC-04-01 | Recommendation Engine | Functional | Age group filtering not applied | Medium | High | Resolved | 2026-05-20 | 2026-05-21 | Recommendation filtering fixed
BR-02 | 3 | TC-01-02 | Authentication | Validation | Invalid credentials not handled clearly | Low | Medium | Resolved | 2026-06-11 | 2026-06-12 | Authentication flow improved
BR-03 | 3 | TC-05-02 | Activity List | UI | Empty result message not informative | Low | Low | Resolved | 2026-05-17 | 2026-05-17 | UX improvement
BR-04 | 4 | TC-03-02 | School Management | Functional | School update changes not saved to database | High | High | Resolved | 2026-02-02 | 2026-02-03 | Missing database commit fixed
BR-05 | 5 | TC-04-01 | Authentication | Security | Expired JWT token not handled correctly | Medium | High | Resolved | 2026-06-11 | 2026-06-12 | Added centralized 401 handling
BR-06 | 6 | TC-04-03 | Gemini Integration | Configuration | Gemini dependency installation failed in CI pipeline | Medium | Medium | Resolved | 2026-05-25 | 2026-05-26 | CI dependency configuration corrected
BR-07 | 7 | TC-05-04 | Activity Management | Functional | Activity planning fields not preserved during update | Medium | Medium | Resolved | 2026-05-27 | 2026-05-27 | Extended planning field support added
BR-08 | 7 | TC-06-02 | AI Adaptation | Functional | Adapted activity difficult to identify after save | Medium | Medium | Resolved | 2026-05-23 | 2026-05-24 | Activity traceability improved
BR-09 | 8 | TC-07-01 | Mobile Integration | Configuration | Android app could not connect to local backend | Medium | Medium | Resolved | 2026-03-27 | 2026-03-29 | Capacitor network configuration updated

## Лист1
Functional | Low | Planned
UI | Medium | Open
Validation | High | Fixed
Performance |  | Verified
Security